## Web
SL | Module/Sub Module/Feature | Build Version/URL | Testing Date | Issue Findings (Issue name, Steps to reproduce, Actual Result, Expected Result, Test Data) | Issue Category | Issue Type | Priority | QA Status | QA Name | Attachment | QA Remarks | Reporting Manager's Feedback | Current Iteration | Issue Occurance Count | Developer Name | Issue Status-Developers Feedback | Developer's Remark | Defect Solved Date
1 | Home > Mobile Platform |  | 1/20/2023 | Actual Result : In the mobile view, design allignment is not okay Steps to Reproduce : 1. Go to : https://sam.rultest.com/user/login 2. Login with valid credential 3. Scroll down Expected Result : In the mobile view, design allignment should be okay | CR | GUI Error | Low | Solved | Ridwan |  | In the mobile view, the circle design and "Mobile Platform" text are overlaping. There should be a distance | Its a valid issue, needs to be fixed |  |  | Arafat | Solved
2 | Home |  | 1/20/2023 | Actual Result : Google Play button does not work Steps to Reproduce : 1. Go to : https://sam.rultest.com/user/login 2. Login with valid credential Expected Result : Google Play button should navigate in to google playstore | Bugs | Functionality Errors | Medium | Open | Ridwan |  | After clicking Google Play button it is staying in the Home page but it shoul navigate to Play store website | Its a valid issue, needs to be fixed, if the link is available |  |  | Arafat | Not Solved | It will be available when app published on playstrore
3 | Home |  | 1/23/2023 | Actual Result : "Module 1 : Introduction" text's all words is in capital letter Steps to Reproduce : 1. Go to : https://sam.rultest.com/user/login 2. Login with valid credential Expected Result : "Module 1 : Introduction" text's all words should not be in capital letter. | CR | Syntactic Error | Low | Solved | Ridwan |  | The text will be "Module 1 : Introduction" instead of "MODULE 1 : INTRODUCTION" | Its a valid issue, needs to be fixed |  |  |  | Solved
4 | Home |  | 1/25/2023 | Actual Result : After maximizing the window Home page, there should be a Close button on the menu bar. Steps to Reproduce : 1. Go to : https://sam.rultest.com/user/login 2. Login with valid credential 3. Minimize the bowser 4. Click the Menu button 5. Maximize the browser Expected Result : After maximizing the window Home page, there should be a Close button on the menu bar. | Bugs | Functionality Errors | High | Solved | Ridwan |  | when we drag the window of the browser and short it and click the menu bar of the website then we click the maximize button of the browser it should be shown as a section. and there should be a close button |  |  |  |  | Solved
5 | Home |  | 1/23/2023 | Actual Result : In the Home page after clicking on the partners logo it does not navigate to their official websites Steps to Reproduce : 1. Go to : https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on the parters logo's Expected Result : In the Home page after clicking on the partners logo it should navigate to their official websites | CR | Navigational Error | Medium | Solved | Ridwan |  | Partnes logo's should be linkable and Clickable | There's no need of fixing this
6 | My Courses |  | 1/25/2023 | Actual Result : In the My Courses page's mobile view option the Menu bar button is missing Steps to Reproduce : 1. Go to : https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on My Courses Expected Result : In the My Courses page's mobile view option the Menu bar button should be there | Bugs | Functionality Errors | High | Solved | Ridwan |  | If we inspect the My courses page in mobile view option the menu bar button disappear |  |  |  |  | Solved
7 | Hom > Course Structure > Module 3 |  | 1/24/2023 | Actual Result : In the home page's Course Structure section Module 3's number ordering are not okay Steps to Reproduce : 1. Go to : https://sam.rultest.com/user/login 2. Login with valid credential 3. Scroll down and go to Course Structure section Expected Result : In the home page's Course Structure section Module 3's number ordering should be okay | CR | Syntactic Error | Medium | Decision Pending | Ridwan |  | The issue is fixed | Its a valid issue, needs to be fixed |  |  | Arafat | Solved | Solved. Please recheck
8 | Courses > Description/Curricullam/FAQ |  | 1/19/2023 | Actual Result : There is no space between Download logo and "Download your Certificate" text Steps to Reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on Courses 4. Click on Enroll Now or Completed Expected Result : There should be a space between Download logo and "Download your Certificate" text | CR | GUI Error | Low | Solved | Ridwan |  |  | ts a valid issue, needs to be fixed |  |  | Arafat | Solved
9 | Courses > Description/Curricullam/FAQ |  | 1/19/2023 | Actual Result : In the course details page if im in Description or FAQ section and reload the page it navigate to Curricullum section Steps to Reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on Courses 4. Click on Enroll Now or Completed Expected Result : In the course details page if im in Description or FAQ section and reload the page it should not navigate to Curricullum section | Bugs | Functionality Errors | High | Solved | Ridwan |  | In the course details page if im in Description or FAQ section and reload the page it should not navigate to Curricullum section | There's no need of fixing this |  |  | Arafat | Solved | Curriculumn tab is default tab.All essential info exist on curriculumn tab.
10 | Courses > Curriculum |  | 1/19/2023 | Actual Result : There are dummy datas in all modules introductions and description Steps to Reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on Courses 4. Click on Curriculum 5. Click on any module Expected Result : There should not be dummy datas in all modules introductions and descripsion | Bugs | Functionality Errors | Medium | Solved | Ridwan |  | In the Curriculum section all Modules description and introductions should be valid text |  |  |  | Arafat | Solved
11 | Courses > Curriculum |  | 1/19/2023 | Actual Result : After completing all module , modeule 2 to 7 does not unlock in curruculum page Steps to Reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on Courses 4. Click on Curriculum 5. Click on any module Expected Result : After completing all module , modeule 2 to 7 should be unlock in curruculum page | Bugs | Functionality Errors | High | Solved | Ridwan | [5 empty] | Arafat | Solved
12 | Courses > Curriculum |  | 1/19/2023 | Actual Result : The FAQ section is empty in Courses Steps to Reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on Courses 4. Click on Curriculum 5. Click on any module Expected Result : The FAQ section should not be empty in Courses | Bugs | Functionality Errors | High | Solved | Ridwan | [5 empty] | Arafat | Solved
13 | Courses > Curriculum |  | 1/19/2023 | Actual Result : The Scroll up button's arrow sign is missing Steps to Reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on Courses 4. Click on Curriculum 5. Click on any module Expected Result : The Scroll up button's arrow sign should be there | CR | GUI Error | Low | Solved | Ridwan | [5 empty] | Arafat | Solved
14 | Courses > Curriculum |  | 1/19/2023 | Actual Result : The "Go to quiz" link does not navigate in quiz page Steps to Reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on Courses 4. Click on Curriculum 5. Click on any module Expected Result : The "Go to quiz" link should navigate in Quiz page | Bugs | Navigational Error | High | Solved | Ridwan | [5 empty] | Arafat | Solved | When Unlock quiz or module, it is not linkable in this page. Vice varca for linkable.
15 | Courses > Curriculum |  | 1/20/2023 | Actual Result : In the Modul 7 page "Quiz Result" link does not navigate in to proper page and showing 500 server error Steps to Reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on Courses 4. Click on Curriculum 5. Go to module 7 Expected Result : In the Modul 7 page "Quiz Result" link should navigate in to proper page and must not show 500 server error | Bugs | Functionality Errors | High | Solved | Ridwan | [6 empty] | Solved
16 | Courses > Curriculum |  | 1/20/2023 | Actual Result : After clicking the start button its allignment is not okay. Steps to Reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on Courses 4. Click on Curriculum 5. Click the start button Expected Result : After clicking the start button its allignment should be okay. | CR | GUI Error | Low | Solved | Ridwan | [6 empty] | Solved
17 | Courses > Module 1 |  | 1/20/2023 | Actual Result : In Module 1 menu buttons options does not work. Steps to Reproduce : 1. Go to: https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on Courses 4. Click the start button 5. Start or Play the video Expected Result : In Module 1 menu buttons options should work. | Bugs | Functionality Errors | Low | Solved | Ridwan |  | Note: In modules Menu bar "Information" and "Exit" button still not working |  |  |  |  | Solved
18 | Courses > Module 1 |  | 1/20/2023 | Actual Result : In mobile view Module 1's presentation slide is too small Steps to Reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on Courses 4. Click the start button Expected Result : In mobile view "Module 1" presentation slide should be visible enough | Bugs | Functionality Errors | Medium | Solved | Ridwan | [6 empty] | Solved
19 | Courses > Module 1 |  | 1/20/2023 | Actual Result : In Mobile view, course modules section "Completed" button and "Next" button's allignment is not okay Steps to Reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on Courses 4. Click the start button Expected Result : In Mobile view, course modules section "Completed" button and "Next" button's allignment is not okay. | CR | GUI Error | Medium | Solved | Ridwan |  | The "Complete" button and the "Next" button should be in same line | its a valid issue, needs to be fixed |  |  |  | Solved
20 | 1. Home>Courses>Login 2. Home>My Courses>Login |  | 1/24/2023 | Actual Result : In the Courses and My Courses page if i want to enroll in the courses it navigate to login page and after login it navigate to home page Steps to Reproduce : 1. Go to :https://sam.rultest.com/ 2. Click on My courses 3. Click on Enroll now 4.Login with valid credential Expected Result : In My Courses page if i want to enroll in the courses it navigate to login page and after login it should navigate to My Courses page | Bugs | Functionality Errors | Medium | Open | Ridwan |  | It is working for courses but not working for my courses.. please check again |  |  |  |  | Solved | redirect to course page/For my course user need to login first. after login them it can go . No redirect required
21 | Profile |  | 1/19/2023 | Actual Result : In the "Age" field negative age number can be select. Steps To reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on User Name beside Resources dropdown button. 4. Click on Profile 5. Select Age in the "Age" field Expected Result : Age can't take a negative value. So it should start from 0. | CR | Functionality Errors | Medium | Solved | Ridwan |  | Note: We are not sure that what will be the starting age ..It may start from 1 but here it is starting from 2 |  |  |  |  | Solved | We give a range from 2 to 100 for web_mobile
22 | Profile |  | 1/19/2023 | Actual Result : There isn't any old/previous password field. Steps To reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on User Name beside Resources dropdown button. 4. Click on Profile Expected Result : User can't update password wothout giving old/previous password. There should be a old/previous password field. | Bugs | GUI Error | Medium | Solved | Ridwan |  | There should be a field of old/ previous password before update new password. |  |  |  |  | Solved
23 | Profile |  | 1/19/2023 | Actual Result : After filling all the field, when update button is being clicked It isn't giving any alert message in the header. Steps To reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on User Name beside Resources dropdown button. 4. Click on Profile Expected Result : After clicking update It should give a message in the header "The profile updated successfully" | Fine Tuning | GUI Error | Medium | Solved | Ridwan |  | Note: The alert message is showing "Profile update successfully" The correct word is "Updated" . It'll look good if "update" word is replaced by "Updated" word | its a valid issue, needs to be fixed |  |  |  | Solved | Profile Updated (As mentioned wasif bhai)
24 | Profile |  | 1/19/2023 | Actual Result : Profile picture section is not working Steps To reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on User Name beside Resources dropdown button. 4. Click on Profile Expected Result : When we select an image it should work fine. | Bugs | Functionality Errors | Medium | Solved | Ridwan | [6 empty] | Solved
25 | Profile |  | 1/19/2023 | Actual Result : There is no heading name in the Profile picture section. Steps To reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on User Name beside Resources dropdown button. 4. Click on Profile Expected Result : There should be a heading "Profile Picture" in the profile picture section. | CR | GUI Error | Medium | Solved | Ridwan |  | In the profile picture Section There should be a heading.. | its a valid issue, needs to be fixed |  |  |  | Solved
26 | Profile |  | 1/23/2023 | Actual Result : When division is selected, All districts are shown in the District Dropdown bar. Steps To reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on User Name beside Resources dropdown button. 4. Click on Profile 5. Select a division 6. Click on District drop down bar. Expected Result : When division is selected, it should show only districts of that particular division. | Bugs | Functionality Errors | Medium | Solved | Ridwan |  | When a division is selected It should show only its districts and Upazila in the dropdown options. |  |  |  |  | Solved
27 | Profile |  | 1/23/2023 | Actual Result : When division and District is selected, All Upazila are shown in the Upazila Dropdown bar. Steps To reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on User Name beside Resources dropdown button. 4. Click on Profile 5. Select a division 6. Click on District drop down bar. Expected Result : When division and district is selected, it should show only Upazila of that particular division. | Bugs | Functionality Errors | Medium | Solved | Ridwan |  | When a division is selected It should show only its districts and Upazila in the dropdown options. |  |  |  |  | Solved
28 | Profile |  | 1/23/2023 | Actual Result : There isn't any dropdown symbol in Gender/ Designation/Institution/Division/District/Upazaila field Steps To reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on User Name beside Resources dropdown button. 4. Click on Profile Expected Result : There should be dropdown symbol in Gender/ Designation/Institution/Division/District/Upazaila field | CR | GUI Error | Medium | Solved | Ridwan |  | If there isn't any dropdown symbol user won't know that it is a dropdown. It looks like a text field. | its a valid issue, needs to be fixed |  |  |  | Solved
29 | Profile |  | 1/23/2023 | Actual Result : Phone number field is taking alphabets as input and it isn't checking boundary value analysis. And there isn't any country code to select. Steps To reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on User Name beside Resources dropdown button. 4. Click on Profile Expected Result : Phone number field should take number as a input only. And It should take 11 digits as a input (For Bangladesh Only) And It should've a option to choose country code. | Bugs | Functionality Errors | Medium | Solved | Ridwan |  | Phone number field should take numbers as a input. It shouldn't take alphabets as a input and It should take valid number (For Bangladesh) as a input And it should check boundary analysis. Such as: A contact number should take 11 (valid number) as input. There should be a option to choose country code. |  |  |  |  | Solved
30 | Profile |  | 1/23/2023 | Actual Result : Full name field is taking numbers as input. Steps To reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on User Name beside Resources dropdown button. 4. Click on Profile Expected Result : Full name field should take alphabets as a input only. | Bugs | Functionality Errors | Medium | Solved | Ridwan |  | Full name field should take alphabets as a input. It shouldn't take number as a input. | its a valid issue, needs to be fixed |  |  |  | Solved
31 | Profile |  | 1/23/2023 | Actual Result : User Name can be set with multiple words . Steps To reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on User Name beside Resources dropdown button. 4. Click on Profile Expected Result : User Name should take Only one words as a input. | Bugs | Functionality Errors | Medium | Solved | Ridwan |  | Normally username can be choose by mixing the name with alphabets and numbers. Username can be set with only one word. Ex: "ridhasan2" It shouldn't take input more than 1 words. Ex: "rid22 hasan 33" |  |  |  |  | Solved
32 | Login |  | 1/23/2023 | Actual Result : There isn't any "Forgot password" feature to recover password. Steps To reproduce : 1. Go to :https://sam.rultest.com/user/login Expected Result : There should be a forgot password feature to recover user password. | CR | GUI Error | Medium | Solved | Ridwan |  | Note: We are not sure that The function to recover password should be "lost password" or not. But "Forgot Password" name is more preferable. |  |  |  |  | Solved | Solve, recheck please
33 | Login |  | 1/23/2023 | Actual Result : It ain't showing any alert message after giving wrong user name and password. Steps To reproduce : 1. Go to :https://sam.rultest.com/user/login Expected Result : After giving wrong user name and password It should give a message in the header: "The User name/password that you've entered is incorrect." | CR | GUI Error | Medium | Solved | Ridwan |  | After login with invalid credentials there should be a alert message.. If email is invalid then it should give a alert message that "Wrong/Invalid email" If the email is valid and password is wrong then It should give a alert message "Wrong password" |  |  |  |  | Solved
34 | Login |  | 1/23/2023 | Actual Result : It ain't showing any alert message after successful login Steps To reproduce : 1. Go to :https://sam.rultest.com/user/login Expected Result : After successful login It should give a message in the header: "Logged in successfully" | CR | GUI Error | Medium | Solved | Ridwan |  | After login with valid credentials it should give a message in the header that "user logged in successfully." | its a valid issue, needs to be fixed |  |  |  | Solved
35 | Resources |  | 1/23/2023 | Actual Result : In the Resources dropdown button, The name of "Weight gain tally sheet for ward" is started with a small letter.. Steps To reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on "Resources" dropdown button in the right upper corner Expected Result : The pdf name of "weight gain tally sheet for ward" should be started with a Capital letter. | CR | GUI Error | Low | Solved | Ridwan |  |  | its a valid issue, needs to be fixed |  |  |  | Solved
36 | Profile |  | 2023-06-02 | Actual Result : After giving invalid name in "Full Name" field, It is showing in the header "The name format is invalid" Steps To reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on User Name beside Resources dropdown button. 4. Click on Profile Expected Result : The header should be " The Full Name format is invalid". | CR | GUI Error | Low | Solved | Ridwan |  | There is two type of name in the profile section. One is User name and another is Full name. So It should be more Specific. |  |  |  |  | Solved
37 | Home |  | 2023-06-02 | Actual Result : There isn't any profile picture icon beside profile name. Steps To reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential Expected Result : After adding a profile picture There should be a profile picture icon beside profile name. | CR | GUI Error | Low | Open | Ridwan |  | Suggestions: Though We don't know the requirements but After adding a profile picture There should be picture icon beside profile name. | [5 empty] | There are no requirement like this
38 | Courses > Modules |  | 2023-06-02 | Actual Result: In all modules, the "Completed" button is not in the right place Steps To reproduce : 1. Go to:https://sam.rultest.com/user/login 2. Login with a valid credential 3. Click on Course 4. Click on "Completed/Enroll" 5. Start a Module Expected Result: In all modules, the "Completed" button should be in the middle | CR | GUI Error | Medium | Solved | Ridwan |  | If the "Completed" button is in the middle it will be more appropriate |  |  |  |  | Solved
39 | Profile |  | 1/23/2023 | Actual Result : The password eye symbol icon works reversely and sometimes it disappears Steps To reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on User Name beside Resources dropdown button. 4. Click on Profile Expected Result : The password eye symbol icon should work in the correct order. | Bugs | Functionality Errors | Medium | Solved | Ridwan | [6 empty] | Solved
40 |  |  |  | Actual Result : When "information button is clicked, new password text field aloignment breaks down. Steps To reproduce : 1. Go to :https://sam.rultest.com/user/login 2. Login with valid credential 3. Click on User Name beside Resources dropdown button. 4. Click on Profile Expected Result : When "information button is clicked, "new password" text field alignment shouldn't break down. | CR | GUI Error | Medium | Solved | Ridwan |  | It should stay in its place and all information should show as a alert message in the header
41 | Home> About the Course |  | 3/20/2023 | Actual Result: Have space before the paragraph Steps To reproduce : 1. Go to:https://sam.rultest.com/user/login 2. Login with a valid credential 3. Home page under the section " about the course" Expected Result: This should have aligned with the whole paragraph. | CR | GUI Error | Medium | Open | Ridwan | [5 empty] | Arafat | Solved |  | 2023-03-21
42 | Home> Course> Details |  | 3/20/2024 | Actual Result: When we mouse hover over the "Description, Curriculum, FAQ" it shows the Text Pointer. Step To Reproduce: 1. Go to:https://sam.rultest.com/user/login 2. Login with a valid credential 3. Click on "Course/My Course" 4. Mouse hover on the "Description, Curriculum, FAQ" Expected Result: Should show "Busy Pointer" or "Link Pointer" | CR | GUI Error | Medium | Open | Ridwan | [5 empty] | Arafat | Solved |  | 2023-03-21
43 | Resources |  | 3/20/2025 | Actual Result: After Downloading the PDF it shows like clockwise rotate Step To Reproduce: 1. Go to:https://sam.rultest.com/user/login 2. Login with a valid credential 3. Click on Resources Expected Result: The downloadable file should be in proper format. | CR | Syntactic Error | High | Open | Ridwan | [7 empty] | Iframe issue
44 | Course> Curriculum> Module |  | 3/20/2026 | Actual Result: In the web view presentation slide view permission Y/N changes in the Mobile view in the opposite way. Step To Reproduce: 1. Go to:https://sam.rultest.com/user/login 2. Login with a valid credential 3. Click on "Course" 4. Click on Module under curriculum 5. Open any course video Expected Result: Should be show same | Bugs | Navigational Error | High | Open | Ridwan | [7 empty] | Iframe issue
45 | Course> Curriculum> Module |  | 3/20/2027 | Actual Result: when we navigate in the mobile mode in any browser it shows as mobile view UI but when we close to inspect it remains the same UI is visible and can able to operate. Step To Reproduce: 1. Go to:https://sam.rultest.com/user/login 2. Login with a valid credential 3. Click on "Course" 4. Click on Module under curriculum 5. Open any course video Expected Result: Should show as web UI | Bugs | Navigational Error | High | Open | Ridwan | [7 empty] | Iframe issue
Ridwan
1 | Active user |  | 2023-03-22 | When a user completes the registration process, s/he is not available in the active users list. | Bugs | Navigational Error | High | Open | Ridwan | [5 empty] | Arafat | Solved |  | 2023-03-22