## Test Report Ridwan
Tracking ID | Module/Sub Module/Feature | Build Version/URL | Testing Date | Issue Findings (Issue name, Steps to reproduce, Actual Result, Expected Result, Test Data) | Issue Category | Issue Type | Priority | QA Status | QA Name | QA Remarks | Attachments | Issue Status-Developers Feedback | Developer's Remark | Reporting Manager's Feedback | Current Iteration | Issue Occurance Count | Developer Name | Defect Solved Date
1 | Notification Access Permission | 1.0.1 | 2023-04-12 | Issue Name: Notification Toggle is being ON after selecting the "Don't Allow" in the Notification Access Permission. Steps: 1. Open the app. 2. Click Don't Allow in the Notification Access Permission. 3. Go to Menu. | Bugs | Functionality Errors | High | Open | Ridwan | The notification toggle should be off if the user clicks "Don't Allow". |  |  | This permission is os permissson | no need
2 | App's ADs | 1.0.1 | 2023-04-12 | Issue Name: Sometimes inappropriate ads appear. Steps: 1. Open the app. | Bugs | Functionality Errors | High | Open | Ridwan | Should not appear any song's related ads as this is an Islamic app. |  |  | need pm deceision | need to change setting of ad mob
3 | Home > Prayer Time | 1.0.1 | 2023-04-13 | Issue Name: After selecting "Only This Time" in the Location Access Permission, The app is not showing the Location Access Permission pop-up every time the app opens or by tapping on the Enable Location Button. Steps: 1. Open the app. 2. Select "Only this time" in the Location Access Permission. | Bugs | Functionality Errors | High | Open | Ridwan | Should appear the Pop-up everytime the app open & click on the Enable Location Button.
4 | Home > Prayer Time | 1.0.1 | 2023-04-13 | Issue Name: After changing the device location by using VPN, the prayer time location is still showing "Dhaka". The location isn't changing. Steps: 1. Open the app. 2. Open a VPN. | Bugs | Functionality Errors | High | Open | Ridwan | The prayer time location should change as device location,
5 | Home > Prayer Time > Today's Prayer Times | 1.0.1 | 2023-04-13 | Issue Name: "Remaining Time" text is touching the circle edge. There should be more padding. Steps: 1. Open the app. 2. Go to Today's Prayer Times. | Fine Tuning | GUI Error | Medium | Open | Ridwan
6 | Home, Category, Favourite > Prayer Time | 1.0.1 | 2023-04-13 | Issue Name: Enable Location Button does not appear sometimes when GPS turns off. Also when GPS turns off the location language translates into Bangla automatically. Steps: 1. Open the app. 2. Turn off the Location of the device. 3. Go to Prayer Time Section. | Bugs | Functionality Errors | High | Open | Ridwan | Should appear the Enable Location Button & Location language should not translate. |  |  | packedge will translate
7 | Favourite | 1.0.1 | 2023-04-13 | Issue Name: After selecting multiple quotes for Favourite, those multiple quotes & arrow icons are not showing in the Favourite Module for the first time. Only the firstly selected module is visible. Users need to swipe on the card so that other selected quotes & arrow icons will appear. Steps: 1. Open the app. 2. Select some Quotes as favourites. 3. Go to Favourite Module. | Bugs | Functionality Errors | High | Open | Ridwan | All selected quotes & arrow icons should appear the first time when a user goes to the Favourite Module.
8 | Full App (Rotate Mode) | 1.0.1 | 2023-04-13 | Issue Name: The app doesn't support rotate mode on mobile devices. But in Tab Devices the app is rotating. That's why some UI is broken. Steps: 1. Open the app. 2. Turn on the Rotate mode on the device. | Bugs | Functionality Errors | High | Open | Ridwan | The app should not rotate on any device.
9 | Full App (Lock Screen Mode) | 1.0.1 | 2023-04-13 | Issue Name: The app is still showing Open on the Lock Screen. Steps: 1. Open the app. 2. Turn on the Rotate mode on the device. | Bugs | Functionality Errors | High | Open | Ridwan | The app should not open in the lock screen.
10 | Menu | 1.0.1 | 2023-04-13 | Issue Name: On the Menu page, in the footer section there has too much void/blank space. Steps: 1. Open the app. 2. Go to Menu. | CR | Functionality Errors | Medium | Decision Pending | Ridwan
11 | Menu > Names of Allah | 1.0.1 | 2023-04-13 | Issue Name: On the Names of Allah page, there shows all 99 names of Allah. But if users tap on the name's card, there has not any audio of the pronunciation of the name. Steps: 1. Open the app. 2. Go to Menu. 3. Go to Names of Allah. | CR | Functionality Errors | Medium | Decision Pending | Ridwan
12 | Menu > Notification | 1.0.1 | 2023-04-13 | Issue Name: After appearing a notification, there has no app favicon in the notification. Steps: 1. Observe the app notification. | CR | Functionality Errors | High | Decision Pending | Ridwan | There should be a favicon of the app
13 | Menu > General Question | 1.0.1 | 2023-04-13 | Issue Name: In the general question third question, there has an alignment problem. Steps: 1. Open the app. 2. Go to Menu. 3. Go to General Question. | Fine Tuning | GUI Error | High | Open | Ridwan
14 | Full App | 1.0.1 | 2023-04-13 | Issue Name: In the app, the header text & back icon isn't in the middle. Steps: 1. Open the app. | Fine Tuning | GUI Error | Low | Open | Ridwan
15 | Menu > General Question | 1.0.1 | 2023-04-13 | Issue Name: In General Question module, All question answers are same . Steps: 1. Open the app. 2. Click on Menu 3. Go to General Question | CR | GUI Error | High | Decision Pending | Ridwan | Questions are different but answers are same. |  |  | Json not provide pm
16 | Menu > Review | 1.0.1 | 2023-04-13 | Issue Name: User can't give rating on review module. Steps: 1. Open the app. 2. Click on Menu 3. Go to Review. | Bugs | Functionality Errors | High | Open | Ridwan |  |  |  | feature will available after published playstore
17 | Menu > About | 1.0.1 | 2023-04-13 | Issue Name: In About, (Facebook, Youtube and Instagram) logo is not redirecting to the links after clicking on them. Steps: 1. Open the app. 2. Click on Menu 3. Go to About. | Bugs | Functionality Errors | High | Open | Ridwan |  |  |  | pm deceision need
18 | Menu > About | 1.0.1 | 2023-04-13 | Issue Name: There is void (Empty Space) in the Downside of the page which doesn't looks user friendly. Steps: 1. Open the app. 2. Click on Menu 3. Go to About. | CR | GUI Error | High | Decision Pending | Ridwan
10
11
12
13
14
15
16
17
18
28
20
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425