## Test Report - Web
| Module/Sub Module/Feature | Build Version/URL | Testing Date | Issue Findings (Issue name, Steps to reproduce, Actual Result, Expected Result, Test Data) | Issue Category | Issue Type | Priority | QA Status | QA Name | Attachment | QA Remarks | Reporting Manager's Feedback | Developer's comment | Current Iteration | Issue Occurance Count | Developer Name | Issue Status-Developers Feedback | Developer's Remark | Defect Solved Date
1 | Header Section - Logo |  | 2023-01-03 | Logos are not responsive | Bugs | Functionality Errors | High | Solved | Ridwan |  | All the logo size should be same
2 | Header Section - Logo |  | 2023-01-03 | Logos are clickable. If user click on the logo, it redirects to the homepage | CR | Navigational Error | Medium | Solved | Ridwan |  | It may go to that particular website and website should open in new tab
3 | Website - Font |  | 2023-01-03 | All the font of the website should be same | CR | GUI Error | Medium | Solved | Ridwan
4 | Landing Page |  | 2023-01-03 | Need to remove extra white space in both side | Bugs | Functionality Errors | High | Solved | Ridwan
5 | Resource |  | 2023-01-03 | This module is not functional | Bugs | Functionality Errors | High | Solved | Ridwan
6 | Resource -> FAQ |  | 2023-01-03 | This module is not functional | Bugs | Functionality Errors | High | Solved | Ridwan
7 | Resource -> User Guide |  | 2023-01-03 | This module is not functional | Bugs | Functionality Errors | High | Solved | Ridwan
8 | Resource -> Training Manual |  | 2023-01-03 | This module is not functional | Bugs | Functionality Errors | High | Solved | Ridwan
9 | Password - Visibility Icon |  | 2023-01-03 | If icon is closed then password is showing and again if icon is open then password is not showing | Bugs | Functionality Errors | High | Solved | Ridwan
10 | Footer |  | 2023-01-05 | Logos are not responsive | Fine Tuning | GUI Error | High | Solved | Ridwan |  | In mobile view, Logos are completely broken
11 | Homepage -> Countdown |  | 2023-01-05 | Countdown section is static. It would be better if the countdown section is dynamic | CR |  |  | Solved | Ridwan |  | Fixed as per requirement, check if design is responsive and ok
12 | Course - Enroll |  | 2023-01-05 | Issue name: After login it redirects to the homepage instead of course details page Steps: 1. Go to COURSES page 2. Click on enroll now 3. Here user is not loggedin. Provide valid credential and click on login button Expected Result: It will redirect to the course details page Actual Result: It will redirect to the home page |  |  |  | Solved | Ridwan
13
14 | Home Page |  | 2023-01-05 | Issue Name: Header Logos are not aligned. Steps: 1. Open elearing Website Expected Result: It should be aligned properly as expected. Actual Result: Logos are not aligned properly on the website. | Fine Tuning | GUI Error | High | Solved | Ridwan |  | Website's Header all logos are not aligned properly. It seems some logos are bigger than others.
15 | Home Page |  | 2023-01-05 | Issue Name: Footer Logos are not aligned. Steps: 1. Open elearing Website Expected Result: It should be aligned properly as expected. Actual Result: Logos are not aligned properly on the website. | Fine Tuning | GUI Error | High | Solved | Ridwan |  | Website's Footer all logos are not aligned properly. It seems some logos are bigger than others.
16 | Home Page |  | 2023-01-05 | Issue Name: All Clickable logos are not directed to the actual webpage. Steps: 1. Open elearing Webpage. 2. Go to the Home Page 3. Click the Clickable logos Expected Result: It should be directed to the actual website. Actual Result: After clicking to the any clickable logo it directed to the "elearning" Homepage. | Bugs | Functionality Errors | High | Solved | Ridwan |  | when we click any of the clickable logos of the header section or footer section, it is directed to the Home page of the website. where it should be directed to the institution's webpage where logos are represented by the individual institutions
17 | Home Page |  | 2023-01-05 | Issue Name: Navigation Bar/Section responsiveness error. Steps: 1. Open elearning website. 2. Click the Browser maximize/minimize button to minimize it. 3. Click the menu bar on the Home page. 4. Again click the maximize/minimize button to maximize it. Expected Result: After maximizing the window Home page navigation should be visualized as the section bar. Actual Result: The home page menu bar remains the same after maximizing the window. | Bugs | Navigational Error | High | Solved | Ridwan |  | when we drag the window of the browser and short it and click the menu bar of the website then we click the maximize button of the browser it should be shown as a section.
18 | Home Page |  | 2023-01-05 | Issue Name: Navigation Bar/Section responsiveness error. Steps: 1. Open elearning website. 2. Click the Browser maximize/minimize button to minimize it. 3. Click the menu bar on the Home page. 4. Again click the maximize/minimize button to maximize it. Expected Result: After maximizing the window Home page, there should be a Close button on the menu bar. Actual Result: There is no Close button on the navigation bar after maximizing the window. | Bugs | Navigational Error | High | Solved | Ridwan |  | when we drag the window of the browser and short it and click the menu bar of the website then we click the maximize button of the browser it should be shown as a section. and there should be a close button.
19 | Home Page |  | 2023-01-05 | Issue Name: Language Conversion doesn't work properly. Steps: 1. Open elearning website 2. Change the language from English to Bangla. Expected Result: In the Home page middle Section(Registered learners, Completed the course, Number of visitors) should be converted to Bangla when it s chosen Bangla front. Actual Result: The home page middle Section(Registered learners, Completed the course, Number of visitors) should not converted to Bangla when it s chosen Bangla front. | Bugs | Syntactic Error | High | Solved | Ridwan
20 | Home Page> Resource |  | 2023-01-05 | Issue Name: Under the Resource Dropdown, all links are inactive. Steps: 1. Open elearning website. 2. Go to the Home page 3. Click the Resource Dropdown 4. Click (FAQ, User Guide, Traning Manual) Expected Result: Should go to the expected links. Actual Result: After clicking all links it directed to the home page. | Bugs | Navigational Error | High | Solved | Ridwan
21 | Home Page> Resource |  | 2023-01-05 | Issue Name: Language Conversion doesn't work properly. Steps: 1. Open elearning website. 2. Go to the Home page 3. Click the Resource Dropdown 4. Change language by clicking English to Bangla. Expected Result: Can be Translated as Bangla words Actual Result: After changing the language to Bangla it shows English words converted as Bangla front. | CR | Syntactic Error | Medium | Solved | Ridwan
22 | Home Page> Resource and My Course |  | 2023-01-05 | Issue Name: Spelling Mistake Steps: 1. Open elearning website. 2. Go to the Home page 3. Click the My Course & Resource Expected Result: It Should be "My Courses" and "Resources" Actual Result: "S" is missing in the "My Courses" and "Resources" | Fine Tuning | Syntactic Error | Medium | Solved | Ridwan
23 | Home Page> Course |  | 2023-01-05 | Issue Name: The title of the course should be shown as the selected language. Steps: 1. Open elearning website. 2. Go to the Home page 3. Click the Course Expected Result: The course title should show English when it's selected English language and as well as It should show Bangla when it's selected Bangla language. Actual Result: It shows Bangla as default. | Bugs | Syntactic Error | Medium | Solved | Ridwan
24 | Home Page> Course> Enroll Course |  | 2023-01-05 | Issue Name: Navigation directed to Home Page as Default. Steps: 1. Open elearning website. 2. Go to the Home page 3. Click the Course 4. Click Enroll Now 5. Give Login Credentials. Expected Result: It should stay Course page after giving the login credentials. Actual Result: After giving the login credentials it directed to the Home Page instead of staying the Course page. | Bugs | Navigational Error | High | Solved | Ridwan
25 | Home Page> Courses> Go to course |  | 2023-01-05 | Issue Name: PopUp Button Change request Steps: 1. Open elearning website. 2. Go to the Home page 3. Click the Course 4. Click Go to course Expected Result: It should be more interactive. Actual Result: Nothing changes visible after clicking the pop-up button. | CR | GUI Error | Medium | Solved | Ridwan
26 | Home Page> Courses> Go to course |  | 2023-01-05 | Issue Name: Navigation directed to the Curriculum section after changing the language. Steps: 1. Open elearning website. 2. Go to the Home page 3. Click the Course 4. Click Go to Course 5. Click any of the sections. Expected Result: It should stay selected section after changing the language. Actual Result: It Changes the direction to the curriculum as default after changing the language. | Bugs | Navigational Error | High | Solved | Ridwan |  | Would like the PM Confirmation
27 | Home Page> Courses> Go to course>Curriculum> Take Quiz |  | 2023-01-06 | Issue Name: The title of "Take Quiz" should translate as the selected language Steps: 1. Open elearning website. 2. Go to the Home page 3. Click the Course 4. Click Go to Course 5. Click Curriculum 6. Click "Take Quiz" Expected Result: Should be Translated when Bangla chooses as a language. Actual Result: It shows "Take Quiz" as default. | CR | Syntactic Error | Medium | Solved | Ridwan
28 | Home Page> Courses> Go to course>Curriculum> Clickable Buttons |  | 2023-01-06 | Issue Name: The title of Clickable Buttons should translate as the selected language Steps: 1. Open elearning website. 2. Go to the Home page 3. Click the Course 4. Click Go to Course 5. Click Curriculum Expected Result: Should be Translated when English chooses as a language. Actual Result: It shows Bangla fronts as default. | CR | Syntactic Error | Medium | Solved | Ridwan
29 | Home Page> Courses> Go to course>Curriculum> Start (Right Side Section) |  | 2023-01-06 | Issue Name: The title of the "Start" section Should translate into Bangla when it chooses as Bangla. Steps: 1. Open elearning website. 2. Go to the Home page 3. Click the Course 4. Click Go to Course 5. Focus on Right side section " Start" 6. Change language from English to Bangla. Expected Result: "Start" Buttons should translate to Bangla when it selected the language English to Bangla. Actual Result: It doesn't translate Bangla when chosse language English to Bangla. | CR | Syntactic Error | Medium | Solved | Ridwan
30 | Home Page> Courses> Go to course>Curriculum> Start (Right Side Section) |  | 2023-01-06 |  |  |  |  | Decision Pending | Ridwan |  | There's not enough data for the test.
31 | My Course |  | 2023-01-05 | Actual Result: In my course page, if we change language multiple time, we have to click back btn multiple time too to navigate to the previous page. Steps To Reproduce: 1. Open elearning website. 2. Go to the Home page 3. Click My Course. Expected Result: We should navigate to the previous page after click the back btn one time. | Bugs | Navigational Error | High | Solved | Ridwan |  | Major issue
32 | My Course > Menu Section |  | 2023-01-05 | Actual Result: In menu section, the title text is in samll letter & "E" is also in small letter in "e-learning" Steps To Reproduce: 1. Open elearning website. 2. Go to the Home page 3. Click My Course. Expected Result: The title text should be in Title Case & "E" should be Capital Letter in "e-learning". | Bugs | GUI Error | High | Solved | Ridwan |  | Major issue
33 | My Course |  | 2023-01-05 | Actual Result: In My Course, after login, we are navigating to the Home Page again. Steps To Reproduce: 1. Open elearning website. 2. Go to the Home page 3. Click My Course. Expected Result: After login in My Course page, we should be nagivate to the My Course page. | Bugs | GUI Error | High | Solved | Ridwan
34 | My Course > Course Card |  | 2023-01-05 | Actual Result: In the course card, the course title isn't translate in english when we set the site language in "English". Steps To Reproduce: 1. Open elearning website. 2. Go to the Home page 3. Click My Course. Expected Result: The course need to translate in English when we set the language in "English" | Bugs | Functionality Errors | High | Solved | Ridwan
35 | My Course > Course Card |  | 2023-01-05 | Actual Result: In the course card, there has no details option about the course. Users need to click the "Go to course" btn for read the details. Steps To Reproduce: 1. Open elearning website. 2. Go to the Home page 3. Click My Course. Expected Result: Need to add a btn or text in the course card, so that the user can easily understand what this course about. | CR | GUI Error | High | Solved | Ridwan
36 | My Course > Go to course |  | 2023-01-05 | Actual Result: In the course details page, the course tittle are not translate in English if we set the language in English. Steps To Reproduce: 1. Open elearning website. 2. Go to the Home page 3. Click My Course. 4. Click Go To Course Expected Result: In the details page, the course tittle should translate in English if we set the language in English. | Bugs | Functionality Errors | High | Solved | Ridwan
37 | My Course > Go to course > Curriculum |  | 2023-01-05 | Actual Result: In Curiculum nav card, the "Unlock" icon is not changing to the "Lock" icon when we click the icon to hide the content. Steps To Reproduce: 1. Open elearning website. 2. Go to the Home page 3. Click My Course. 4. Click Go To Course Expected Result: "Unlock" icon should change to "Lock" icon after we click in for hide the content | Bugs | GUI Error | High | Solved | Ridwan
38 | My Course > Go to course > Curriculum |  | 2023-01-05 | Actual Result: In Curiculum nav card, "Take Quiz" & "Title" is not understandable if we should click it or not. Steps To Reproduce: 1. Open elearning website. 2. Go to the Home page 3. Click My Course. 4. Click Go To Course Expected Result: Need to add different color in "Take Quiz" & "Title". | CR | GUI Error | High | Solved | Ridwan |  | Text color & font weight are not change yet.
39 | My Course > Go to course > Description |  | 2023-01-05 | Actual Result: In Description nav, if we change the language or refresh the page, we are redirected to the Curiculum nav again. Steps To Reproduce: 1. Open elearning website. 2. Go to the Home page 3. Click My Course. 4. Click Go To Course Expected Result: After changing language or refresh the page, it should redirected to the description nav. | Bugs | Functionality Errors | High | Solved | Ridwan |  | Would like to PM's Confirmation
40 | My Course > Go to course > Learning Object |  | 2023-01-05 | Actual Result: In Learning Object nav, if we change the language or refresh the page, we are redirected to the Curiculum nav again. Steps To Reproduce: 1. Open elearning website. 2. Go to the Home page 3. Click My Course. 4. Click Go To Course Expected Result: After changing language or refresh the page, it should redirected to the Learning Object nav. | Bugs | Functionality Errors | High | Solved | Ridwan |  | Would like to PM's Confirmation
41 | My Course > Go to course | URL | 2023-01-05 | We don't have proper requirment about "Start", "Enrolled", "Lecture" section. |  |  |  |  | Akib | ScreenShot |  | These are test data. Will check ones the product is live |  | 2
42 | Username Dropdown -> Profile |  | 2023-01-05 | Actual Result: Organization name, Designation value, Gender value, Age value does not translate into Bangla Steps To Reproduce: 1. Go to the WHO website URL: https://whodev.rultest.com/user/profile 2. Verify that system should redirect to the Home Page. 3. Login with valid credential HRS ID : 302 Password : 1234 2. Click on the Profile dropdown bar. Expected Result: Organization name, Designation value, Gender value, Age value should translate into Bangla | Bugs | Functionality Errors | Medium | Solved | Ridwan |  | bug fixed
43 | Username Dropdown -> Profile |  | 2023-01-05 | Actual Result: Image upload option logo and label is not in right place Steps To Reproduce: 1. Go to the WHO website URL: https://whodev.rultest.com/user/profile 2. Verify that system should redirect to the Home Page. 3. Login with valid credential HRS ID : 302 Password : 1234 4. Click on the Profile dropdown bar. Expected Result: Organization name, Designation value, Gender value, Age value should translate into Bangla | CR | GUI Error | Medium | Solved | Ridwan |  | issue fixed
44 | Username Dropdown -> Profile |  | 2023-01-05 | Actual Result: Password and change password visiblity eye simbol works reverse. Steps To Reproduce: 1. Go to the WHO website URL: https://whodev.rultest.com/user/profile 2. Verify that system should redirect to the Home Page. 3. Login with valid credential HRS ID : 302 Password : 1234 4. Click on the Profile dropdown bar. Expected Result: Password and change password visiblity eye simbol should not works reverse. | Bugs | Functionality Errors | Medium | Solved | Ridwan |  | Bug fixed
45 | Username Dropdown -> Profile |  | 2023-01-05 | Actual Result: Footer logos is not responsive in mobile view Steps To Reproduce: 1. Go to the WHO website URL: https://whodev.rultest.com/user/profile 2. Verify that system should redirect to the Home Page. 3. Login with valid credential HRS ID : 302 Password : 1234 2. Click on the Profile dropdown bar. Expected Result: Footer logos should be responsive in mobile view | Bugs | GUI Error | High | Solved | Ridwan |  | fixed
46 | Username Dropdown -> Profile |  | 2023-01-05 | Actual Result: Comma missing in contact details before Mohakhali. Steps To Reproduce: 1. Go to the WHO website URL: https://whodev.rultest.com/user/profile 2. Verify that system should redirect to the Home Page. 3. Login with valid credential HRS ID : 302 Password : 1234 4. Click on the Profile dropdown bar. Expected Result:There should be a comma in contact details before Mohakhali. | Fine Tuning | Syntactic Error | Low | Solved | Ridwan
47 | Username Dropdown -> Profile |  | 2023-01-05 | Actual Result: In the profile form age up-down button it is taking minus (-) input Steps To Reproduce: 1. Go to the WHO website URL: https://whodev.rultest.com/user/profile 2. Verify that system should redirect to the Home Page. 3. Login with valid credential HRS ID : 302 Password : 1234 4. Click on the Profile dropdown bar. Expected Result:In the profile form age up-down button it should not take minus (-) input | Bugs | Functionality Errors | High | Solved | Ridwan |  | The previous issue is fixed. But as we do not know the requirement it is taking 0 to infinity number for Age input
48 | Username Dropdown -> Profile -> Update |  | 2023-01-05 | Actual Result: After updating the password it does not login with updated password Steps To Reproduce: 1. Go to the WHO website URL: https://whodev.rultest.com/user/profile 2. Verify that system should redirect to the Home Page. 3. Login with valid credential HRS ID : 302 Password : 1234 4. Click on the Profile dropdown bar. 5. Update password 6. Login with updated password Expected Result: After updating the password it should be login with updated password | Bugs | Functionality Errors | High | Solved | Ridwan |  | Could not retest the data validation of the Profile page, because the profile page edit option might be not be in the requirement.
49 | My Courses |  | 2023-02-08 | Issue: The course card's are now in vertically. & also don't have any margin between two cards. Steps To Reproduce: 1. Go to the WHO website URL: https://who.elearning.rultest.com/# 2. Verify that system should redirect to the Home Page. 3. Login with valid credential HRS ID : 302 Password: 1234 4. Click Courses/My courses. | CR | GUI Error | High | Solved | Ridwan |  | The course card's can be set in horizontally with good margin.
50 | Username Dropdown -> Profile -> Update |  | 2023-02-08 | Actual Result: There is no profile picture header in the profile picture section Steps To Reproduce: 1. Go to the WHO website URL: https://whodev.rultest.com/user/profile 2. Verify that system should redirect to the Home Page. 3. Login with valid credential HRS ID : 302 Password : 1234 4. Click on the Profile dropdown bar. Expected Result: There should be a profile picture header in the profile picture section | CR | GUI Error | Low | Solved | Ridwan
51 | Login |  | 2023-02-13 | Issue: In login page, after change the language in Bangla, The login form's Lebels are not translating in Bangla. STR: 1. Go to the URL | Bugs | Functionality Errors | High | Solved | Ridwan
52 | Login |  | 2023-02-13 | Issue: In login page, the inputboxes has no placeholder. STR: 1. Go to the URL | Fine Tuning | GUI Error | High | Solved | Ridwan |  | For better user experience there should be placeholder in the inputboxes | [7 empty] | 2023-03-02
53 | Home |  | 2023-02-13 | Issue: The counter number is showing english, after change the language in Bangla. STR: 1. Go to the URL 2. Login with credentials | Bugs | Functionality Errors | Medium | Solved | Ridwan
54 | Home |  | 2023-02-13 | Issue: The counter title is not in Title Case(Every words first letter Should be Capital). STR: 1. Go to the URL 2. Login with credentials | CR | GUI Error | Low | Solved | Ridwan |  | If the Counter title is be like "Registered Learners", then the UI will look more eye catching.
55 | Home |  | 2023-02-13 | Issue: The Bangla font is looking very standard & eye catching. STR: 1. Go to the URL 2. Login with credentials | CR | GUI Error | Low | Solved | Ridwan |  | Can be use some Eye-catching & Standard Bangla Font like "Kalpurush" or something like that.
56 | Home > (Responsive Mode) |  | 2023-02-13 | Issue: Contact section has no right-margin in responsive mode. STR: 1. Go to the URL 2. Login with credentials | Fine Tuning | GUI Error | Medium | Solved | Ridwan |  | Contact Section should be in center.
57 | Home > (Responsive Mode) |  | 2023-02-13 | Issue: In "ABOUT THE PLATFORM' Section, the two pics has no margin between them. STR: 1. Go to the URL 2. Login with credentials | Fine Tuning | GUI Error | Medium | Solved | Ridwan
58 | Home > Footer |  | 2023-02-13 | Issue: In footer section, Contact section & "Design & Developed By Riseup Labs" Text are in same line. STR: 1. Go to the URL 2. Login with credentials | CR | GUI Error | High | Solved | Ridwan |  | "Design & Developed By Riseup Labs" text should be in the bottom & middle align. Not in same line with contact section.
59 | Courses |  | 2023-02-13 | Issue: After click the Course, in navigation bar, the navigation bar's & some others font in body section are changing to another font. STR: 1. Go to the URL 2. Login with credentials 3. Click Courses. | Fine Tuning | GUI Error | High | Solved | Ridwan |  | All font should be same in navigation bar.
60 | My Courses > Go To Course |  | 2023-02-13 | Issue: The title "SQA TESTING" has too much top-Padding. The extra void is looking odd. STR: 1. Go to the URL 2. Login with credentials 3. Click My Courses. 4. Click Go To Course. | Fine Tuning | GUI Error | Low | Solved | Ridwan |  | The top-padding size can be use as like Courses or My courses page's title.
61 | My Courses > Go To Course |  | 2023-02-13 | Issue: In the nav, Curriculum has a active-color. But if users click the other two nav, the active-color isn't showing for that others nav. STR: 1. Go to the URL 2. Login with credentials 3. Click My Courses. 4. Click Go To Course. | Fine Tuning | GUI Error | Medium | Solved | Ridwan |  | The issue is still there | [7 empty] | 2022-02-03
62 | My Courses > Go To Course > (Responsive Mode) |  | 2023-02-13 | Issue: After click the "Learning Objects", the contect is out of the box & the card title is overlapping with the icon. Not responsive. STR: 1. Go to the URL 2. Login with credentials 3. Click My Courses. 4. Click Go To Course. | Fine Tuning | GUI Error | High | Solved | Ridwan
63 | My Courses > Go To Course |  | 2023-02-13 | Issue: After change the language in Bangla, Some Text isn't translating. STR: 1. Go to the URL 2. Login with credentials 3. Click My Courses. 4. Click Go To Course. | Bugs | Functionality Errors | Medium | Solved | Ridwan | [9 empty] | 2022-02-03
64 | My Courses > Go To Course |  | 2023-02-13 | Issue: Start btn text is not translating properly & also there has some spelling mistake, after change the language in Bangla. STR: 1. Go to the URL 2. Login with credentials 3. Click My Courses. 4. Click Go To Course. | Fine Tuning | GUI Error | High | Solved | Ridwan |  | বক্তৃতা spelling is not change yet. | [7 empty] | 2022-02-19
68 | My Courses |  | 2023-02-15 | Issue: If a course is unpublished by Admin, that course is not showing in Courses Module. But the course is still showing in My Courses Module. STR: 1. Go to the URL 2. Login with credentials 3. Click My Courses. | Bugs | Functionality Errors | High | Solved | Ridwan |  | By requirement, that course shouldn't visible in the My Course Module.
69 | Resources > FAQ |  | 2023-02-14 | Issue: The Card's title is not align in middle of the box vertically. STR: 1. Go to the URL 2. Login with credentials 3. Click Resources. 4. Click FAQ. | Fine Tuning | GUI Error | Low | Solved | Ridwan
70 | Resources > FAQ |  | 2023-02-14 | Issue: The Page title "COURSE FAQ" color is not matched with other pages color. STR: 1. Go to the URL 2. Login with credentials 3. Click Resources. 4. Click FAQ. | Fine Tuning | GUI Error | Low | Solved | Ridwan |  | It will be more eye catching if all header titles color will be same. | [7 empty] | 2023-03-02
71 | Resources > USER GUIDE |  | 2023-02-14 | Issue: The pdf frame is too small. User can't see the whole page of the pdf. User need to scroll the pdf to read one page of the pdf. STR: 1. Go to the URL 2. Login with credentials 3. Click Resources. 4. Click USER GUIDE. | Fine Tuning | GUI Error | High | Solved | Ridwan |  | The pdf frame height should be incress so that user can see a whole page without scroll.
72 | Resources > (Responsive Mode) |  | 2023-02-14 | Issue: In responsive mode, in the menu, the resourses dropdown is not working. STR: 1. Go to the URL 2. Login with credentials 3. Click Resources. | Bugs | Functionality Errors | High | Solved | Ridwan
73 | Profile |  | 2023-02-14 | Issue: In profile info box, The Keys/Titles are not translating when user change the language in Bangla. STR: 1. Go to the URL 2. Login with credentials 3. Click Profile. | Bugs | Functionality Errors | High | Solved | Ridwan
74 | Guest Login |  | 2023-02-14 | Issue: After login as a guest, user can go to courses and go to lectures STR: 1. Go to the URL 2. Login as Guest 3. Click Profile. | Bugs | Functionality Errors | High | Solved | Ridwan |  | Don't know the requirement of Guest login
79 | Courses |  | 2023-02-16 | Issue: On the quiz result page it does not translate English to Bangla STR: 1. Go to the URL 2. Login with credentials 3. Click Courses. 4. Complete the quiz | Bugs | Functionality Errors | Medium | Solved | Ridwan |  | solved in dev server | [7 empty] | 2023-03-02
79 | Courses>Quiz | URL | 2023-02-15 | Need Quiz answers to finish the module and test it.
80 | Certificate |  | 2023-02-24 | Issue: There is no course header(name) in the certificate list STR: 1. Go to the URL 2. Login with credentials 3. Click on certificate | CR | GUI Error | Medium | Solved | Ridwan |  | It's confusing, don't know which certificate im downloading | [7 empty] | 2023-03-02
81 | My Courses > Go to course |  | 2023-02-24 | Issue: If a user goes to "go to course"/Course details page after enrolling in a course, then if the admin deletes that course, the site breaks after reloading. STR: 1. Go to the URL 2. Click My Courses. 3. Click Got to course. | Bugs | Functionality Errors | High | Solved | Ridwan |  | In the Attachment video after "30 Sec" the admin deleted that course from the admin panel which is not visible in this video. But after "34 Sec" you can see that after reloading that page the site crashed. ** After reload the page there should be a "404" page or should redirect to the My Courss Page instead of a broken page. ** | [7 empty] | 2023-03-02
82 | My Courses > Go to course |  | 2023-02-24 | Issue: If a user goes to "go to course" after enrolling in a course, then if the admin unpublished that course, that course details page still showing in the website & also user can start that course. Even if the user reloads the tab, that course details page is still visible. But If the user navigate to my courses or courses page then that course is not visible. STR: 1. Go to the URL 2. Click My Courses. 3. Click Got to course. | Bugs | Functionality Errors | High | Solved | Ridwan |  | In this Attachment, video user is already on the Course Details page. But the admin unpublished that course from the Admin panel which is not visible in this video. ** After reloading the page, there should be a "404" page or redirect to the My Courses Page. ** | [7 empty] | 2023-03-02
83 | My Courses > Go to course > (Responsive Mode) |  | 2023-02-24 | Issue: In "Curriculum" nav, the card's title is overlapping with Icon. STR: 1. Go to the URL 2. Click My Courses. 3. Click Got to course. | Bugs | GUI Error | High | Solved | Ridwan |  | There should be some padding between the title & icon.
84 | Certificate |  | 2023-02-24 | Issue: In the Certificate list without selecting any address from the dropdown bar, the certificate is generated without an address STR: 1. Go to the URL 2. Login with credentials 3. Click on the certificate 4. Click on Submit | Bugs | GUI Error | High | Solved | Ridwan |  | There should not be any option to download or generate a certificate without selecting any address | [7 empty] | 2023-03-01
85 | Certificate |  | 2023-02-27 | Issue: In the Certificate list page's mobile responsive mode, address drop-down bar alignment is not okay STR: 1. Go to the URL 2. Login with credentials 3. Click on the certificate 4. Go to mobile responsive mode 5. Click on select one | CR | GUI Error | Medium | Solved | Ridwan |  | its okay in mobile | [7 empty] | 2023-03-01
86 | Course > Course Module |  | 2023-02-27 | Issue: Completed module successfully message does not stay long to read properly. STR: 1. Go to the URL 2. Login with credentials 3. Click on the certificate 4. Go to mobile responsive mode 5. Click on select one | CR | GUI Error | Medium | Solved | Ridwan | [9 empty] | 2023-03-01
87 | Footer |  | 2023-02-27 | Issue: In footer section, the Contact Details section is out of Safe area. STR: 1. Go to the URL 2. Login with credentials | Bugs | GUI Error | Medium | Solved | Ridwan
88 | Header |  | 2023-02-27 | Issue: In the navigation bar, courses and my courses bangla translation is not okay STR: 1. Go to the URL 2. Login with credentials | Bugs | Functionality Errors | Medium | Solved | Ridwan | [9 empty] | 2023-03-01
89 | Guest Login |  | 2023-02-27 | Issue: Appropriate message should show while login as a guest | CR | GUI Error | Medium | Solved | Ridwan |  | It should be Guest Login Successfull | [7 empty] | 2023-03-01
90 | Course > Course Module |  | 2023-02-28 | Issue: After ending the minimum time in a module the page refreshes itself | Bugs | Functionality Errors | High | Solved | Ridwan |  | the page should not refresh | [7 empty] | 2023-03-01
91 | Profile |  | 2023-02-28 | Issue: There is no size limit in the profile picture upload | Bugs | Functionality Errors | High | Solved | Ridwan | [9 empty] | 2023-03-01
92 | Home |  | 2023-02-28 | Issue: Could not test the Registered learners and Completed the course numbers because we don't have multiple credential |  |  | Medium | Solved | Ridwan
93 | Guest Logout |  | 2023-02-28 | Issue: If I click guest logout more than 2 times the page show an unauthorized error | Bugs | Functionality Errors | High | Solved | Ridwan | [9 empty] | 2023-03-01
93 | Navigation bar |  | 2023-03-10 | Issue: If the user hover over the navigation bar, it is moving in the Bangla version but in the English version it's okay | Bugs | GUI Error | High | Solved | Ridwan
94 | Home |  | 2023-03-10 | Issue: In the home page introduction section the Bangla translation is not okay | CR | Syntactic Error | High | Solved | Ridwan | [9 empty] | 2023-03-12
95 | Courses > Marksheet |  | 2023-03-10 | Issue: In the Marksheet page there is no Go to course or Back button | CR | Functionality Errors | High | Solved | Ridwan
96 | Courses > Quiz |  | 2023-03-10 | Issue: After completing the modules if a user fails a quiz ,user can go to the quiz again without completing the modules first | Bugs | Functionality Errors | High | Solved | Ridwan |  | The modules should be locked if a user fails a quiz, user should not be able to take the quiz again without completing the module first
97 | Courses > Quiz |  | 2023-03-10 | Issue: If a user fails a quiz and go the Marksheet page and clicks the browser back button the user can give the quiz again | Bugs | Functionality Errors | High | Solved | Ridwan |  | user should not retake the quiz again from mark sheet page
98 | Resources > Trainer Guide |  | 2023-03-10 | Issue: There is no video title in the Trainer Guide page | CR | GUI Error | High | Solved | Ridwan | [9 empty] | 2023-03-12
99 | Course > Course Module |  | 2023-03-10 | Issue: In the mobile view version, pdf is not showing in the course module Same issue is in User Guide pages pdf | Bugs | Functionality Errors | High | Solved | Ridwan |  | PDF must show | [7 empty] | 2023-03-12
100 | Resources > Trainer Guide |  | 2023-03-10 | Issue: In the trainer guide page if a user input the wrong password and then tries to input another password the submit button do not work | Bugs | Functionality Errors | High | Solved | Ridwan |  | submit button must work | [7 empty] | 2023-03-12
101 | Courses > Module |  | 2023-03-13 | Issue: After completing the minimum time in a course module, the side module name became unclickable from clickable | Bugs | Functionality Errors | High | Solved | Ridwan | [9 empty] | 2023-03-14
102 | Navigation Bar |  | 2023-02-22 | Issue: In the navigation bar, is showing "My Courses". STR: 1. Verify that the system should redirect to the Home Page. | Fine Tuning | GUI Error | High | Solved | Ridwan |  | It should be shown "My Course"
103 | Profile |  | 2023-02-28 | Issue: If the user uploads a big-size picture in the profile picture, the website can't handle it. | Bugs | Functionality Errors | High | Solved | Ridwan |  | I uploaded a 7.2 MB size picture. I wrote the same type of issue before (tracking id 91)
104 | Courses > Module |  | 2023-02-28 | Issue: In the course module, If the user clicks the next button and goes to the next module the "Course Details" menu bar opens the 1st module instead of the current module | Bugs | Navigational Error | High | Solved | Ridwan
105 | FAQ |  | 2023-02-28 | Issue: Training spelling mistake | CR | Syntactic Error | Medium | Solved | Ridwan
105 | Certificate |  | 2023-04-17 | Issue: Certificate spelling mistake | CR | Syntactic Error | High | Open | Ridwan