## GEO
Staff | Module/Sub Module/Feature | Build Version/URL | Testing Date | Issue Findings (Issue name, Steps to reproduce, Actual Result, Expected Result, Test Data) | Issue Category | Issue Type | Priority | QA Status | QA Name | QA Remarks | Attachments | Reporting Manager's Feedback | Current Iteration | Issue Occurance Count | Developer Name | Issue Status-Developers Feedback | Developer's Remark | Defect Solved Date
1 | Geo > Divisions > Search Bar |  | 2023-01-09 | Actual result: In search bar, the title "Action" is not properly translating when user set the language in "BN". Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on the Geo > Division button Expected Result: "Action" text should be translate properly when user set the language in "BN". | Bugs | Functionality Errors | Medium | Open | Ridwan
2 | Geo > Divisions > Search Bar |  | 2023-01-09 | Actual result: In search btn, the buttonText "Search" is not translating when user set the language in "BN". Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on the Geo > Division button Expected Result: The buttonText "Search" should be translate when user set the language in "BN". | Bugs | Functionality Errors | Medium | Open | Ridwan
3 | Geo > Divisions > Search Bar |  | 2023-01-09 | Actual result: In search bar, the placeholder is "Search". Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on the Geo > Division button Expected Result: "Search" is not properly understandable which data should use for search. | CR | GUI Error | High | Decision Pending | Ridwan | Placeholder should be like "Search by ID" or "Search by name" etc.
4 | Geo > Divisions > Search Bar |  | 2023-01-09 | Actual result: After search something, there has no back button to navigate previous page easily. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on the Geo > Division button | CR | GUI Error | Low | Decision Pending | Ridwan | There should be a "Back btn" which redirected user to the main division page.
5 | Geo > Divisions > Search Bar |  | 2023-01-09 | Actual result: After search, user need to delete the previously searched data on the textbox by clicking the backspace btn, if user want to type new data for search. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on the Geo > Division button | CR | GUI Error | Medium | Decision Pending | Ridwan | If there will be a "Cross" icon in search textbox to delete the previously searched data in one click, this will be more user friendly.
6 | Geo > Divisions |  | 2023-01-09 | Actual result: After user navigate in Divisions page, if user change the language multiple time, user need to click the "Back btn" multiple time also to navigate to the previous page. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on the Geo > Division button Expected Result: After clicking back btn one time, it should redirect user to the previous page. | Bugs | Functionality Errors | High | Open | Ridwan
7 | Geo > Divisions |  | 2023-01-09 | Actual result: In table, the "Table Head" is not translating when we set the language in "BN" Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on the Geo > Division button Expected Result: "Table Head" should be translate when we set the language in "BN". | Bugs | Functionality Errors | Medium | Open | Ridwan
8 | Geo > Divisions |  | 2023-01-09 | Actual result: In table, the "Status" & "Action btn texts" are not translating in Bangla after user set the language "BN". Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on the Geo > Division button Expected Result: It should be translate when user set the language in "BN", | Bugs | Functionality Errors | Medium | Open | Ridwan
9 | Geo > Divisions > Add New |  | 2023-01-09 | Actual result: In Add New, the error messages showing on the top of the page. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on the Geo > Division button 4. Click on the Add New button Expected Result: The error messages should shows below to the each textInput field. | CR | GUI Error | Low | Decision Pending | Ridwan
10 | Geo > Divisions > Add New |  | 2023-01-09 | Actual result: After add new division, Edit division & delete division, the "Success" response message stack/stayed in the page permanently. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on the Geo > Division button 4. Click on the Add New button 5. Add/Edit/Delete data. 6. Click on Save. Expected Result: The response message should be vanish after few seconds. | Bugs | Functionality Errors | High | Open | Ridwan
11 | Geo > Divisions > Add New |  | 2023-01-09 | Actual result: After add new division, the "ID" number is not maintaining its serial. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on the Geo > Division button 4. Click on the Add New button 5. Add some data. 6. Click on Save. Expected Result: "ID" number should be maintaining in right serial. | Bugs | Functionality Errors | High | Open | Ridwan
12 | Geo->Districts-> Add/Edit |  | 2023-01-09 | Actual Result: In the View or Edit page if the languange option change to English to Bangla or Bangla to English then the back button does not work. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on Geo dropdown bar. 4. Click Distritcs 5. Clink on add or edit button 6. Change Bangla to English or English to Bangla 7. Click back button Expected Result: In the View or Edit page if the languange option change to English to Bangla or Bangla to English then the back button should work. | Bugs | Navigational Error | High | Open | Ridwan
13 | Geo->Districts |  | 2023-01-09 | Actual Result: There is no suggetion text for what to search in the search box Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on Geo dropdown bar. 4. Click Distritcs option Expected Result: There should be a suggetion text for what to search in the search box | CR | GUI Error | Low | Decision Pending | Ridwan
14 | Geo->Districts |  | 2023-01-09 | Actual Result: Table head name does not translate into bangla after changing English to Bangla Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on Geo dropdown bar. 4. Click Distritcs option Expected Result: Table head name should translate into bangla after changing English to Bangla | Bugs | Functionality Errors | Medium | Open | Ridwan
15 | Geo->Districts |  | 2023-01-09 | Actual Result: After searching something and then clearing the search data from search box it does not show all datas. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on Geo dropdown bar. 4. Click Distritcs option 5. Search something and then clear searched data. Expected Result: After searching something and then clearing the search data from search box it should show all datas | CR | GUI Error | Medium | Decision Pending | Ridwan
16 | Geo->Districts |  | 2023-01-09 | Actual Result: Action and Status options does not translate into bangla in Bangla language option. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on Geo dropdown bar. 4. Click Distritcs option Expected Result: Action and Status should translate into bangla in Bangla language option. | Bugs | Functionality Errors | Medium | Open | Ridwan
17 | Geo->Districts->View |  | 2023-01-09 | Actual Result: In the view page back button does not translate in bangla Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on Geo dropdown bar. 4. Click Distritcs option 5. Click View button Expected Result: In the view page back button does not translate in bangla. | Bugs | Functionality Errors | Medium | Open | Ridwan
18 | Geo->Districts->Edit |  | 2023-01-09 | Actual Result: Update response message should show in the edit page instead of previous page Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on Geo dropdown bar. 4. Click Distritcs option 5. Click Edit button 6. Update info and save Expected Result: In the view page back button does not translate in bangla. | CR | GUI Error | Medium | Decision Pending | Ridwan
19 | Geo->Districts->Edit |  | 2023-01-09 | Actual Result: UEdit and Add form take Bangla input in English name feild and take English input in Bangla name. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on Geo dropdown bar. 4. Click Distritcs option 5. Click Edit button 6. Update info and save Expected Result: In the view page back button does not translate in bangla. | Bugs | Functionality Errors | High | Open | Ridwan
20 | Geo->Districts->Edit |  | 2023-01-09 | Actual Result: Edit form is updating with empty lat and lon feild Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on Geo dropdown bar. 4. Click Distritcs option 5. Click Edit button 6. Update info without any data in lat and lon feild and save Expected Result: Edit form should not be updated with empty lat and lon feild | Bugs | Data validation | High | Open | Ridwan
21 | Geo->Districts->Edit |  | 2023-01-09 | Actual Result: Edit form is updating with invalid lat , lon and url data Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on Geo dropdown bar. 4. Click Distritcs option 5. Click Edit button 6. Update info with invalid data in lat, lon and url feild and save Expected Result: Edit form should not update with invalid lat , lon and url data | Bugs | Data validation | High | Open | Ridwan
22 | Geo->Upazilla / City Corporation |  | 2023-01-09 | Actual Result: In the Geo dropdown bar Upazilla spelling and in the header portion of Upazilla/City Corporation page Upazilla spelling are not correct. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Select the Geo dropdown bar. 4. Select the Upazilla / City Corporation sub-module. 5. See the Upazilla/City Corporation button & the header portion. Expected Result: Geo dropdown bar Upazilla spelling and in the header portion of Upazilla/City Corporation page Upazilla spelling should be correct. | CR | GUI Error | Medium | Decision Pending | Ridwan | The correct spelling of Upazilla is 'Upazila'
23 | Geo->Upazilla / City Corporation |  | 2023-01-09 | Actual Result: Need to clear the previous search data by using the backspace button. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Select the Geo dropdown bar. 4. Select Upazilla/City Corporation 5. Click the search button after giving any data in the search bar. Expected Result: A cancel button should be shown in the search bar. Test Data: hdfhgd | Bugs | Functionality Errors | Medium | Open | Ridwan | If the search option is user friendly then it will be better.
24 | Geo -> Upazilla / City Corporation |  | 2023-01-09 | Actual result: Search button, Sl,Upazilla ID,District ID, Name,Bn Name,Url,Status, Action all are not translating into bangla when the user set the language in "BN". Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Select the Geo dropdown bar. 4. Select Upazilla/City Corporation sub-module. 5. Click EN button and select "BN". Expected Result: Search button, Sl,Upazilla ID,District ID, Name,Bn Name,Url,Status, Action all are should be translated into bangla when the user set the language in "BN". | Bugs | Functionality Errors | Medium | Open | Ridwan
25 | Geo->Upazilla / City Corporation->Add new |  | 2023-01-09 | Actual Result: In the Add new page if the language option change from English to Bangla or Bangla to English 2/3 times then the back button does not work. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on Geo dropdown bar. 4. Click Upazilla/City Corporation button. 5. Click on Add new 6. Change Bangla to English or English to Bangla 2/3 times. 7. Click the back button. Expected Result: The back button should be worked after changing English to Bangla or Bangla to English 2/3 times. | Bugs | Navigational Error | High | Open | Ridwan | The back button must work.
26 | Geo -> Upazilla / City Corporation |  | 2023-01-09 | Actual Result: If the user fills the input field with previously saved/same data the new Upazilla/City Corporation is added successfully. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on Geo dropdown bar. 4. Click Upazilla/City Corporation button. 5. Click on Add new 6. Input the previous data. 7. Click the save button. Expected Result: The new Upazilla/City Corporation should not be added successfully If the user fills the input field with previously saved/same data. | Bugs | Data validation | High | Open | Ridwan
27 | Geo -> Upazilla / City Corporation |  | 2023-01-10 | Actual Result: If the user gives the Bangla text in Name (In English) section and English text in Name(In Bangali) section it is saved successfully. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on Geo dropdown bar. 4. Click Upazilla/City Corporation. 5. Click on Add new 6.Give the input Bangla text in Name (In English) section and English text in Name(In Bangali) section. 7. Click save button. Expected Result: It should not be saved successfully if the user gives the Bangla text in Name (In English) section and English text in Name(In Bangali) section. Test Data: Name (In English): টেস্ট০১ Name (In Bengali): test01 | Bugs | Data validation | High | Open | Ridwan
28 | Geo -> Upazilla / City Corporation |  | 2023-01-10 | Actual Result: If the user gives any data just like a special character( !/@) in Add new input field it is saved successfully. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on Geo dropdown bar. 4. Click Upazilla/City Corporation. 5. Click on Add new 6. Give any data just like special character( !/@) in Add new input field. 7. Click the save button. Expected Result: It should not be saved successfully if the user gives any data just like a special character( !/@) in Add new input field. Test Data: Name (In English): ! Name (In Bengali): ! Url: ! | Bugs | Data validation | High | Open | Ridwan
29 | Geo -> Upazilla / City Corporation |  | 2023-01-10 | Actual Result: All right reserved in the bottom don't show properly below the page size 665px * 734.40px. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on Geo dropdown bar. 4. Click Upazilla/City Corporation. 5. Reduce he page size below 565px * 734.40px Expected Result: All right reserved should be shown properly below the page size 565px * 734.40px. | Bugs | GUI Error | Medium | Open | Ridwan | All right reserved should be in one line & there need some space between 'All right reserved' & 'Dessigned & Developed by Riseup Labs'.
30 | Geo -> Upazilla / City Corporation |  | 2023-01-10 | Actual Result: In the view section District Id, Name, Bn Name, Url and Status don't convert in Bangla when users select the 'BN'. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on Geo dropdown bar. 4. Click Upazilla/City Corporation. 5. Click the view underneath of Action. 6. See the District Id, Name, Bn Name, Url, Status. Expected Result: District Id, Name, Bn Name, Url and Status should be converted in Bangla in the view section when users select the 'BN'. | Bugs | GUI Error | Medium | Open | Ridwan | At least District Id, Name, Bn Name, Url, Status should be shown in Bangla when user select select the 'BN'
31 | Geo -> Upazilla / City Corporation |  | 2023-01-10 | Actual Result: The pagination is shown on left side. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on Geo dropdown bar. 4. Click Upazilla/City Corporation. 5. See the pagination. Expected Result: If the pagination will show in the Middle then it will be better. | CR | GUI Error | Low | Decision Pending | Ridwan
32 | Geo -> Upazilla / City Corporation |  | 2023-01-10 | Actual Result: There is no suggestion text for what to search in the search box Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Select the Geo dropdown bar. 4. Select Upazilla / City Corporation 5. Write down any letter/word in the search field. Expected Result: There should be a suggestion text for what to search in the search box | CR | GUI Error | Low | Decision Pending | Ridwan | Search field isn't user friendly.
33 | Geo->Upazilla / City Corporation |  | 2023-01-10 | Actual Result: The pagination doesn't show properly below the page size 565px * 734.40px. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Reduce he page size below 565px * 734.40px Expected Result: The pagination should be shown properly below the page size 565px * 734.40px. | Bugs | GUI Error | Medium | Open | Ridwan | The pagination goes outside the card/Container.
34 | Geo -> Union/Thana |  |  | Actual Result: In the Union/Thana, If we search by any ID number , It doesn't show any match result. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Select the Geo dropdown bar. 4. Select Union/Thana 5. In the search box give a ID Number as a input. Then click Search button. Expected Result: After giving a ID as a input in the Search box . It should show the details of an user if the ID matches. If ID not matches with any ID number then It should show No data. | Bugs | Functionality erros | medium | open | Ridwan | There should be a suggestion that user should search by which data.
35 | Geo -> Union/Thana |  |  | Actual Result: In the Union/Thana, After searching a data If we want to search another data we need to clear the previous search data by using backspace button. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Select the Geo dropdown bar. 4. Select Union/Thana 5. In the search box give a ID Number as a input. Then click Search button. Expected Result: After giving a ID as a input in the Search box .It should show a cross button to clear the data from search box. | Bugs | GUI Error | medium | Open | Ridwan | There should be a clear(*) button to clear all the data at once from search box.
36 | Geo -> Union/Thana |  |  | Actual Result: In the Union/Thana, If we search by any Sl. number , It doesn't show any match result. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Select the Geo dropdown bar. 4. Select Union/Thana 5. In the search box give a Sl. Number as a input. Then click Search button. Expected Result: After giving a Sl. number as a input in the Search box, It should show the details of the given Sl. no user. if not matches it should show No data. | Bugs | Functionality erros | medium | open | Ridwan | There should be a suggestion that user should search by which data.
37 | Geo -> Union/Thana |  |  | Actual Result: In the Union/Thana, After searching a value there isn't any back button to go to previous page. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Select the Geo dropdown bar. 4. Select Union/Thana 5. In the search box give a input. Then click Search button. Expected Result: After searching data there should be a back button to go to previous page. | Bugs | Navigational Error | medium | open | Ridwan
38 | Geo -> Union/Thana |  |  | Actual Result: In the Union/Thana, After clearing the previous search data from the search box, It isn't showing previous all data Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Select the Geo dropdown bar. 4. Select Union/Thana 5. In the search box give a input. Then click Search button. Expected Result: After clearing data from search box it should show the default first page values. | Bugs | GUI Error | medium | open | Ridwan
39 | Geo -> Union/Thana |  |  | Actual Result: In the dashboard, the name of "Geo" Module changed into "place". Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. Expected Result: The name of the module shouldn't be changed. | CR | Functionality erros | medium | Decision Pending | Ridwan | In the home page when translation button is clicked (En to BN), page reloads and The name of "Geo" module changed into "Place". After reloading sometime It isn't changing back to Geo.
40 | Geo -> Union/Thana |  |  | Actual Result: In the dashboard, the name of "Observation" Module changed into "assessment". Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. Expected Result: The name of the module shouldn't be changed. | CR | Functionality erros | medium | Decision Pending | Ridwan | In the home page when translation button is clicked (En to BN), page reloads and The name of "Observation" module changed into "assessment". After reloading sometime It isn't changing back to Observation.
41 | Geo -> Union/Thana |  |  | Actual Result: In the dashboard, the name of "Teachers" Module changed into "The teachers". Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. Expected Result: The name of the module shouldn't be changed. | CR | Functionality erros | medium | Decision Pending | Ridwan | In the home page when translation button is clicked (En to BN), page reloads and The name of "Teachers" module changed into "The teachers". After reloading sometime It isn't changing back to Observation.
42 | Geo -> Union/Thana -> Geo/place |  |  | Actual Result: In the dashboard, the name of "Divisions" Module changed into "department". Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. Expected Result: The name of the module shouldn't be changed. | CR | Functionality erros | medium | Decision Pending | Ridwan | In the dashboard, when translation button is clicked (En to BN), page reloads and The name of "Divisions" module changed into "department". After reloading sometime It isn't changing back to "Divisions".
43 | Geo -> Union/Thana |  |  | Actual result: In the Union/Thana, "Search" button is not translating when user set the language in "BN". Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Select the Geo dropdown bar. 4. Select Union/Thana 5. Click EN button in top right corner and select "BN". Expected Result: "Search" button should be translate when user set the language in "BN". | Bugs | Functionality Errors | Medium | Open | Ridwan | EN to BN Should work properly. It isn't user friendly.
44 | Geo -> Union/Thana |  |  | Actual result: In the Union/Thana, The header( Sl., Id,Upazilla ID, Name,Bn Name,Url,Status, Action) is not translating. translating when user set the language in "BN". Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Select the Geo dropdown bar. 4. Select Union/Thana 5. Click EN button in top right corner and select "BN". Expected Result: The header( Sl., ID ,Upazilla ID, Name,Bn Name,Url,Status, Action) should be translate after clicking BN button. | Bugs | Functionality Errors | Medium | Open | Ridwan | EN to BN Should work properly. It isn't user friendly.
45 | Geo -> Union/Thana |  |  | Actual result: In the Union/Thana, "View" button ,"Edit" button, "Delete" button is not translating when user set the language in "BN". Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Select the Geo dropdown bar. 4. Select Union/Thana 5. Click EN button in top right corner and select "BN". Expected Result: "View" button ,"Edit" button, "Delete" button should be translate when user set the language in "BN". | Bugs | Functionality Errors | Medium | Open | Ridwan | EN to BN Should work properly. It isn't user friendly.
46 | Geo -> Union/Thana |  |  | Actual result: Active/Inactive buttontext of "Status" column is not translating when user set the language in "BN". Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Select the Geo dropdown bar. 4. Select Union/Thana 5. Click EN button in top right corner and select "BN". Expected Result: Active/Inactive buttontext should be translate when user set the language in "BN". | Bugs | Functionality Errors | Medium | Open | Ridwan | EN to BN Should work properly. It isn't user friendly.
47 | Geo -> Union/Thana |  |  | Actual Result: There is no suggetion text for what to search in the search box Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Select the Geo dropdown bar. 4. Select Union/Thana 5. Click view/edit button. Expected Result: There should be a suggetion text for what to search in the search box. | CR | GUI Error | Low | Decision Pending | Ridwan | There should be a suggestion that user should search by which data.
48 | Geo -> Union/Thana |  |  | Actual Result: In the View or Edit page, the previous page biutton does not work if the languange option change to EN to BN/ BN to EN. Steps To reproduce: 1. Enter the credential on the login page. Gmail: admin@admin.com password:1234 2. Verify that system should redirect to the Dashboard. 3. Click on Geo dropdown bar. 4. Click Distritcs 5. Clink on add or edit button 6. Change Bangla to English or English to Bangla 7. Click back button Expected Result: In the View or Edit page if the languange option change to English to Bangla or Bangla to English then the back button should work. | Bugs | Navigational Error | High | Open | Ridwan | EN to BN Should work properly. It isn't user friendly.
49
50
51
52
53
54
55
56
57
58
59
60
61
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425